## SPA's
Strategic Planning Area | # | # Projects per SPA | Affected Communities | Bordered By | Fire Protection Agency | Wildfire Jurisdiction | Risk Level
Benton County | ALL | 22 | County-Wide Initiatives
Urban Area | 1 | 21 | Corvallis Albany Philomath Adair Village | E- Willamette River W- SPA #3 N- Polk Co S- SPA #2 | Corvallis Fire Department Albany Fire Department Adair Rural Fire Protection District Philomath Fire & Rescue | Oregon Department of Forestry | Low
Farm Area | 2 | 3 | Monroe Alpine Alpine Junction Bellfountain Greenberry | E- Willamette River & Linn Co W- Dense Forest N- SPA #1 S- Lane Co | Monroe Rural Fire Protection District Philomath Fire & Rescue Corvallis Fire Department | Oregon Department of Forestry | Variable Depending on Location/relative to WUI
Northern Forest Area | 3 | 31 | Kings Valley Soap Creek Hoskins Wren | W- SPA #4 N- Polk Co E & S- SPA #1 | Hoskins-Kings Valley Rural Fire Protection District Philomath Fire & Rescue Corvallis Fire Department Adair Rural Fire Protection District | Oregon Department of Forestry | Variable Depending on Location/Relative to WUI
Western Forest Area | 4 | 11 | Summit Blodgett Dawson Glenbrook | E- SPA #2 & SPA #3 W- SPA #5 & Lincoln Co N- Polk Co S- Lane Co | Blodgett-Summit Rural Fire Protection District Philomath Fire & Rescue Monroe Rural Fire Protection District | Oregon Department of Forestry | Moderate-High
Coastal Range | 5 | 6 | Alsea | N & W- Lincoln Co S- Lane Co E-SPA #4 | Alsea Rural Fire Protection District | Oregon Department of Forestry | Moderate-High

## Projects by SPA
SPA | Category/Type | Update Year | Priority | Timeline | Project Name | Project | # Acres | # of Structures | Miles of Road | Length (feet) | Current Owner | Existing Right-of-Way | Lead Agency | Support Agency List | 2023 Status
ALL | Capability Enhancement | 2023 |  | Ongoing | Funding for Mitigation Projects | Improve mitigation capabilities by developing a more stable funding mechanism for mitigation and education activities outside of the regular operating budget of local fire districts. | [6 empty] | Benton County Community Development
ALL | Capability Enhancement | 2023 |  |  | Water Source Aparatus | Obtain funding to purchase the equipment needed to ensure interoperability of fire aparatus and water sources across fire agencies (ex. Couplings and fittings) | [6 empty] | Benton County Fire Defense Board |  | New 2023
ALL | Fire Prevention, Education & Mitigation | 2023 | High |  | Mitigation & Recovery Coordinator | TBD | [6 empty] | Benton County Community Development
ALL | Fire Prevention, Education & Mitigation | 2023 | Medium | 2 years | BCFDB Wildfire Publication | Create and distribute a newsletter format publication that is available to Benton County residents | [6 empty] | Benton County Sheriff's Office-EM | Benton County Fire Defense Board
ALL | Fire Prevention, Education & Mitigation | 2023 | High | Ongoing | Firewise Education Programs | Work with ODF, OSU Extension, and others to offer Firewise education programs to assist landowners on creating and maintaining fireresistant defensible space and Firewise landscaping around structures. | [6 empty] | Benton County Community Development | Oregon Department of Forestry OSU Extension | Ongoing; 2016 update notes: Most education has been conducted by county and ODF personnel, due to administrative changes at OSU Extension. Due to overlap and similar purposes, the two items above and several wildfire education items from the 2009 CWPP have been combined into one.
ALL | Fire Prevention, Education & Mitigation | 2023 | Medium | Ongoing | Neighborhood Chipping and Recycling Program | In cooperation with homeowners’ groups, operate a multi-site neighborhood chipping program for materials generated by fuels mitigation projects. | [6 empty] | Benton County Community Development | Benton County CD | This program is only available for Firewise communities or those in the process of becoming a Firewise community. 2016 update notes: A chipping program in multiple locations throughout the county has been established, and is managed by ODF, with chipping performed on contract with local providers. The local recycling center partnership with drop boxes was determined unfeasible. Instead, drop locations are established in many locations, private landowners haul the fuels they collect, and chipping dates are scheduled. This item will be retained and revised. The Community Development coordinator has taken over coordination of this task from ODF. The chipping program is ongoing, subject to budget appropriations.
ALL | Fire Prevention, Education & Mitigation | 2023 | High | Ongoing | Homesite Risk Evaluations | Prepare for wildfire events in high risk areas (homes in the WUI) by conducting homesite risk assessments and developing area-specific “Response Plans” to include participation by all affected jurisdictions and landowners. | [6 empty] | Oregon Department of Forestry | Benton County CD | Risk evaluations are only completed for prospective Firewise communities
ALL | Fire Prevention, Education & Mitigation | 2023 | Medium | Ongoing | Inter-Agency Coordination | Fuels reduction projects, both completed and planned, should be listed and mapped. | [6 empty] | Benton County Community Development
ALL | Fire Prevention, Education & Mitigation | 2023 |  | Ongoing | Youth Wildfire Education | Implement a youth based wildfire education program; fire agency based | [6 empty] | Benton County Fire Defense Board |  | Adult wildfire education programs were initiated, however youth specific programs were not.
ALL | Infrastructure Enhancements | 2023 |  | Ongoing | Private Bridge Signage | Rate and Sign all private bridges countywide | [6 empty] | Benton County Public Works |  | 2016 update notes: An inventory of all private bridges in the county was completed, performed by ODF staff, and each bridge’s photographs and characteristics recorded and mapped by county GIS. Load rating was found to be unfeasible due to cost, and signage has been posted by individual fire districts in selected location. The inventory of bridges was accomplished and will be removed from the action items list; and the rating and signage will be revised and added as Action Item 3.
ALL | Infrastructure Enhancements | 2023 | High | 3 years | Radio Interoperability Update | Implement the radio infrastructure projects identified in the Radio Infrastructure Assessment | [6 empty] | Multi-Agency Coordination |  | Benton County Sheriff's Office (BCSO) had a Radio Infrastructure Assessment completed in 2022. Projects identified need grant funding for completion. BCSO- Grant Application for funding of projects Linn-Benton Radio Interoperability Group (LBRIG)- 700mHz system and maintenance of system Corvallis Regional Communications Center (CRCC)- VHF and maintenance of system
ALL | Infrastructure Enhancements | 2023 | Medium | 2 years | Water Source Inventory | Map, develop GIS database, and provide signage for onsite water sources such as hydrants, underground storage tanks, and drafting or dipping sites on all ownerships across the county. | [6 empty] | Benton County GIS | BC Fire Defense Board Oregon Department of Forestry Benton County CD Benton County GIS | 2016 update notes: Staff of ODF mapped onsite natural water sources county-wide. Remaining developed water sources need to be mapped and signed.
ALL | Infrastructure Enhancements | 2023 |  | Ongoing | Evacuation Route Inventory | Inventory, map, and sign all potential evacuation routes | [6 empty] | Benton County GIS |  | 2016 update notes: This has been partially completed, with signage on the evacuation routes that have been constructed. Evacuation routes in limited access neighborhoods have emerged as an issue of primary importance during the next CWPP cycle.
ALL | Infrastructure Enhancements | 2023 |  | Ongoing | Evactuation Route Education | Educate the public on emergency evacuation routes throughout the County | [6 empty] | Benton County Sheriff's Office-EM |  | 2023 update: Combined Coordination of Evacuation Awareness project description into Evacuation Route Inventory and Evacuation Route Education projects
ALL | Infrastructure Enhancements | 2023 |  | Ongoing | Substandard Bridge and Culvert Improvements | Make access improvements to substandard bridges and culverts and limiting road surfaces on public and private rights-of-way not already identified. | [6 empty] | Benton County Public Works |  | Skunk Creek culvert - replaced a failing structure Public Works plans to replace the Oak Creek bridge on Oak Creek Drive
ALL | Infrastructure Enhancements | 2023 |  |  | Wildfire Protection Management Plan | Develop wildfire protection-specific management plan, including a fuels reduction program, for the City of Corvallis Watershed and adjacent properties. | [6 empty] | Corvallis Fire Department |  | 2016 update notes: This issue has been a concern of fire protection agencies and was addressed in the 2013 update of the Corvallis Forest Stewardship Plan by the City of Corvallis.
ALL | Safety & Policy | 2023 | Medium | 2 years | Private Bridge Education | Assist fire districts in educating private landowners about the wildfire risks associated with structurally inadequate bridges and substandard driveways that hamper emergency response. | [6 empty] | Benton County Fire Defense Board | Fire Mashals of Districts/Departments | This has been done with us on a spot-basis, generally, when there is a permit pulled for dwelling improvements or on emergency calls. The Fire Districts will undertake a three year project to rate all access roads including bridges and culverts
ALL | Safety & Policy | 2023 |  |  | Firewise Community Education | Distribute Firewise-type educational brochures with building permit applications | [6 empty] | Benton County Community Development |  | Ongoing
ALL | Safety & Policy | 2023 | High | 2 years | Formation of New Districts | Assess areas currently outside of existing fire districts for annexation or formation of new district due to increasing population or high fire risk. | [6 empty] | Benton County Fire Defense Board | County Board of Commissioners | Initial studies and public contact with residents of the Greenberry Gap indicated an unfavorable climate for annexations by adjoining fire districts, due to response times, budgetary constraints, and overtaxing volunteer departments that are already stretched thin. Discussions with residents, firefighting professionals, and county personnel turned towards the idea of the formation of a new district in the Gap, and efforts were undertaken to explore implementation of this strategy. Added to the 2016 Update task list. There was little support from the property owners to create a new district. However, the new SB 762 bill requires that all lands have a baseline level of fire protection by January 2026 so some action will be taken regardless of property owner hesitation.
ALL | Safety & Policy | 2023 |  |  | Coordination of Evacuation Plans | Continue pre-planning emergency evacuation routes with specifications for all-hazard scenarios | [6 empty] | Benton County Sheriff's Office-EM |  | New 2023
ALL | Safety & Policy | 2023 |  |  | Prescribed Burning | Support prescribed burning as an effective tool to reduce hazardous fuels in the WUI within applicable regulations | [6 empty] | Oregon Department of Forestry |  | New 2023
ALL | Safety & Policy | 2023 |  |  | Pre-Disaster Contracts | Prepare pre-disaster contracts; traffic flagging for evacuations of Timberhill area and general contracts in preparation of a large wildfire | [6 empty] | Benton County Public Works |  | New 2023
SPA 1 | Access Improvement | 2023 |  |  | Dawnwood Drive | Dawnwood Drive to Panorama connectivity |  |  |  | 6436 | Private | No | Benton County Public Works | All Local Fire Department/Districts | No update
SPA 1 | Access Improvement | 2023 |  |  | Ponderosa Ridge | Ponderosa Ridge to Oak Creek connectivity |  |  |  | 3514 | OSU | No | Benton County Public Works | All Local Fire Department/Districts | No update
SPA 1 | Access Improvement | 2023 |  |  | Skyline West Subdivision | Widen Access Roads, Improve Access Road Connectivity, Extension of Municipal Water System | 283 | 220 | 2.9 |  |  |  | City of Corvallis- Any Department | All Local Fire Department/Districts | Secondary access to the neighborhood created through NW Fair Oaks Drive Project underway to build emergency connection to NW Oak Creek Drive
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Arboretum Road | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 160 | 93 | 1.9 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | North Albany #1 Springhill, Winn, Picadilly Roads | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 152 | 98 | 2.5 |  |  |  | Albany Fire Department | All Local Fire Department/Districts
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | North Albany #2 Palestine Road | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 143 | 77 | 2.8 |  |  |  | Albany Fire Department | All Local Fire Department/Districts
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | North Albany #3 Valley View Area | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 290 | 225 | 1.2 |  |  |  | Albany Fire Department | All Local Fire Department/Districts
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | North Albany #4 Rondo Street to N. Albany Road | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 653 | 357 | 5.6 |  |  |  | Albany Fire Department | All Local Fire Department/Districts
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Grand Oaks Subdivision Commons #1 | Fuel reduction in the common and surrounding areas of the subdivision; | 20 | [5 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Grand Oaks Subdivision Commons #2 | Removal of invasive species, brush and ladder-fuel treatment coupled with replanting of native prairies and oak woodland species | 20 | [5 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | N. Albany Hwy 20 Route | Fuel reduction along the highway; trim and remove trees and underbrush growing near the road | [6 empty] | Albany Fire Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Bessie Coleman Elementary School | Provide fuel reduction to increase defensible space around the school | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Brandis Natural Area | Fuel reduction throughout the natural area | 10 | [5 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Benton County Fairgrounds | Fuel reduction to increase defensible space surrounding the grounds | [6 empty] | Benton County Natural Areas & Parks Dept | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | NW Oak Grove Drive | Fuels reduction/trimming from NW Oaks Grove Dr from West of Oak Grove School to Metge Lane | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Witham Hill Drive #1 | Fuels reduction/trimming along Witham Hill Drive between NW Walnut and NW 36th | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Circle Blvd | Fuels reduction/trimming along Circle between Witham Hill Drive and NW Calliope | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | West Hills Road | Fuels reduction/trimming along W Hills Road between Grand Oaks subdivision and Reservoir Road | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Fire Prevention, Education & Mitigation | 2023 |  |  | Witham Hill Drive #2 | Install additional turnout and/or widen access road on NW Witham Hill Dr at the top of the hill | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Infrastructure Enhancements | 2023 |  |  | NW Ponderosa Ave | Place several fire hydrants along the avenue, extending into Skyline West neighborhood | [6 empty] | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 1 | Infrastructure Enhancements | 2023 |  |  | Rosecrest Estates | Add 2 or 3 hydrants in Rosecrest Estates and connect to community well located on Rosecrest Drive near the intersection of Primrose Loop | [6 empty] | Philomath Rural Fire Protection District | All Local Fire Department/Districts | New 2023; Philomath Rural Fire Protection District should be involved in the testing and location of water sources
SPA 2 | Access Improvement | 2023 |  |  | Airport Avenue | Improve structural defensible space, improve access road connectivity- Airport to Greasy Creek | 674 | 26 |  | 9617 | County | Yes | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 2 | Fire Prevention, Education & Mitigation | 2023 |  |  | Monroe | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 791 | 371 | 6.6 |  |  |  | Monroe Rural Fire Protection District | All Local Fire Department/Districts | New 2023
SPA 2 | Safety & Policy | 2023 | High | 2 years | Greenberry Gap Fire District | Assess areas currently outside of existing fire districts for annexation or formation of new district due to increasing population or high fire risk. | [6 empty] | County Board of Commissioners | BC Fire Defense Board | There was little support from the property owners to create a new district. However, the new SB 762 bill requires that all lands have a baseline level of fire protection by January 2026 so some action will be taken regardless of property owner hesitation.
SPA 3 | Access Improvement | 2023 |  |  | Northwest Cardwell Hill Drive | Cardwell East to Cardwell West connectivity |  |  |  | 14296 | County | Yes | Philomath Rural Fire Protection District | Corvallis Fire Department Wren Disaster Preparedness Co.
SPA 3 | Access Improvement | 2023 |  |  | Cardwell-Panorama Connector | Cardwell to Panorama connectivity |  |  |  | 5160 | County | Yes | Philomath Rural Fire Protection District | Corvallis Fire Department Wren Disaster Preparedness Co. | No update
SPA 3 | Access Improvement | 2023 |  |  | Mitchell Drive | Waneta to Mitchell connectivity |  |  |  | 932 | County/Private | Partial | Benton County Public Works | All Local Fire Department/Districts | No update
SPA 3 | Access Improvement | 2023 |  |  | Tansy Extension | Tansy Drive to Garrett connectivity |  |  |  | 607 | County/Private | Partial | Benton County Public Works | All Local Fire Department/Districts | Ongoing
SPA 3 | Access Improvement | 2023 |  |  | Panorama Extension | Panorama to Dawnwood Drive connectivity |  |  |  | 2058 | County | Yes | Benton County Public Works | All Local Fire Department/Districts | No update
SPA 3 | Access Improvement | 2023 |  |  | Heritage Hills Road | 9th to Panorama connectivity |  |  |  | 11494 | Private | No | Benton County Public Works | All Local Fire Department/Districts | No update
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Cardwell Hill- Oak Creek | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity, Improve Substandard Bridges | 1714 | 575 | 16.6 |  |  |  | Benton County Public Works | All Local Fire Department/Districts
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Soap Creek Road | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity, Improve Substandard Bridges | 2457 | 250 | 11.6 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | Wristman Creek Road bridge was replaced by Starker
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Marys River Estates | Install Additional Turnouts and/or Turnaround Areas, Conduct Fuels Reduction Treatments | 983 | 191 | 6.2 |  |  |  | Benton County Public Works | All Local Fire Department/Districts
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Wren Community | Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity, Improve Substandard Bridges | 2100 | 284 | 10.4 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Trillium Lane | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 393 | 60 | 3.1 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Coffn Butte Road | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity | 320 | 34 | 1.1 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | As part of a proposal to expand Coffin Butte Landfill, Coffin Butte Road may be vacated and alternative routes improved for regular traffic, emergency response, and evacuation
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  | Ongoing | Wren Fire Substation | Fuels reduction around the substation- defensible space | [6 empty] | Philomath Rural Fire Protection District | All Local Fire Department/Districts | Philomath Rural Fire Protection District has partnered with the Landowner-acts as a Long Term Lease tenant to manage this project
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Wren Community Hall | Fuel reduction around Wren Community Hall including driveway expansion to accommodate evacuees and emergency response staging and fire suppression equipment | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | McDonald Forest #1 | Fuel reduction in WUI's between McDonald Forest and residential spaces | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Bald Hill Natural Area | Fuel reduction across the area | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Mary's River Estates Road | Improve defensible space through fuel reduction along the highway; trim or remove trees and underbrush that grows near the roadway | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Blakesley Creek Road | Fuel reduction along the roadway | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Soap Creek Schoolhouse #1 | Fuel reduction to increase defensible space surrounding the schoolhouse | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | South Boundary Road #2 | Fuels reduction/trimming along South Boundary Road | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Soap Creek Road #1 | Fuels reduction/trimming along Soap Creek Road from Sulphur Springs to Tampico Road | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Soap Creek Road #2 | Fuels reduction/trimming along Soap Creek Road from Fire Substation over Vineyard Mountain/Lewisburg Saddle | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Fire Prevention, Education & Mitigation | 2023 |  |  | Tampico Road | Fuels reduction/trimming along Tampico Road from Soap Creek Road to Hwy 99 | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Infrastructure Enhancements | 2023 |  |  | Wildwood Road Hydrant | Install a pumped hydrant on Wildwood Road | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | 2016 update notes: This item remains a desired infrastructure improvement in the H-KV District, and like other localized concerns is best removed and added to the department’s list of future projects for which to seek funding and staff time.
SPA 3 | Infrastructure Enhancements | 2023 |  |  | Maxfield Creek Road Hydrant | Install a pumped hydrant on Maxfield Creek Road | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | 2016 update notes: This item remains a desired infrastructure improvement in the H-KV District, and like other localized concerns is best removed and added to the department’s list of future projects for which to seek funding and staff time.
SPA 3 | Infrastructure Enhancements | 2023 |  |  | Kings Valley Mill Hydrant | Install a pumped hydrant on the downtown Kings Valley Mill site | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | 2016 update notes: This item remains a desired infrastructure improvement in the H-KV District, and like other localized concerns is best removed and added to the department’s list of future projects for which to seek funding and staff time.
SPA 3 | Infrastructure Enhancements | 2023 |  |  | Soap Creek Schoolhouse #2 | Install a water source | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Infrastructure Enhancements | 2023 |  |  | Soap Creek Substation | Install a water source | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 3 | Infrastructure Enhancements | 2023 |  |  | South Boundary Road #1 | Install 2 water sources for fire access | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023- contact Pam Wilson for information
SPA 3 | Safety & Policy | 2023 | High | 1 year | Wren to Cardwell Hill Evac Route | Develop an Emergency Evacuation Plan for the Wren to Cardwell Hill area- maintenance of drivable route and development of inter-agency coordinated strategy | [6 empty] | Benton County Sheriff's Office-EM | Benton County CD All Locall Fire Department/Districts | The facility has been placed on the FEMA RISKMap priority list for maintenance
SPA 3 | Safety & Policy | 2023 | High | 1 year | Wren to Cardwell Hill Evac Route | Develop an Emergency Evacuation Plan for the Wren to Cardwell Hill area- public information campaign | [6 empty] | Benton County Sheriff's Office-EM | Benton County CD All Locall Fire Department/Districts | The facility has been placed on the FEMA RISKMap priority list for maintenance
SPA 4 | Access Improvement | 2023 |  |  | Upepr Ridenour Creek | Improve Access Road Connectivity | 1013 | 37 | 4.6 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Pioneer Village | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads, Improve Access Road Connectivity, Reduce Structural Ignitability Factors | 241 | 66 | 3.1 |  |  |  | Benton County Public Works | All Local Fire Department/Districts
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Blodgett to Summit | Improve Structural Defensible Space (including Blodgett school), Install Additional Turnouts and/or Widen Access Roads, Improve Substandard Bridges | 1688 | 137 | 7.6 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | Bridge on NW Oak Creek Drive to be replaced in 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Corvallis Watershed | Hazardous Fuels Reduction and Forest Health Improvement | 2354 | 10 | 1.2 |  |  |  | City of Corvallis- Any Department | All Local Fire Department/Districts | New 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | West Blodgett | Improve Structural Defensible Space, Install Additional Turnouts and/or Widen Access Roads | 1023 | 72 | 7.5 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | Bridged Removed- Updated Project list
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Norton Creek Road | Improve structural defensible space, improve access road connectivity | 2661 | 31 |  |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Old Peak Road | Improve structural defensible space, improve access road connectivity | 1495 | 70 |  |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Beaver Creek Road | Improve structural defensible space, improve access road connectivity | 1622 | 44 |  |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Botkin Road | Improve structural defensible space, improve access road connectivity | 279 | 23 |  |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 4 | Fire Prevention, Education & Mitigation | 2023 |  |  | Foster Road #2 | Reduction of fuels along Foster Road | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 4 | Resource Enhancement | 2023 |  |  | Foster Road #1 | Place water tanks for firefighters along Foster Road and it's "feeder" roads | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 5 | Fire Prevention, Education & Mitigation | 2023 |  |  | Cecil Lane | Widen Access Road, Roadside Fuels Treatments, Install Additional Turnouts and/or Turnarounds | 179 | 22 | 1.6 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 5 | Fire Prevention, Education & Mitigation | 2023 |  |  | Honey Grove Road | Improve structural defensible space, improve access road connectivity | 1246 | 19 |  |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 5 | Fire Prevention, Education & Mitigation | 2023 |  |  | Alsea Town Water Storage | Improve defensible space surrounding the water tank | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 5 | Fire Prevention, Education & Mitigation | 2023 |  |  | Alsea Stout Well | Improve defensible space surrounding the well | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 5 | Infrastructure Enhancements | 2023 |  |  | Lobster Creek | Bridge Replacement | 283 | 3 | 7.6 |  |  |  | Benton County Public Works | All Local Fire Department/Districts | New 2023
SPA 5 | Resource Enhancement | 2023 |  |  | Alsea Chipper Program | Purchase and mobilize a chipper for the Alsea Community | [6 empty] | Benton County Public Works | All Local Fire Department/Districts | New 2023

## Projects by Fire Agency
SPA | Lead Agency | Category/Type | Update Year | Project | 2023 Status | Column1 | Column2
ALL | ALL Benton County Fire Districts-Departments | Resource & Capability Enhancements | 2023 | Improve mitigation capabilities by developing a more stable funding mechanism for mitigation and education activities outside of the regular operating budget of local fire districts.
ALL | ALL Benton County Fire Districts-Departments | Resource & Capability Enhancements | 2023 | Develop additional water resource sites to supplement fire suppression efforts throughout Benton County.
ALL | ALL Benton County Fire Districts-Departments | Resource & Capability Enhancements | 2023 | Improve departmental capability by establishing a program to increase the retention and recruitment of volunteer firefighters.
ALL | ALL Benton County Fire Districts-Departments | Resource & Capability Enhancements | 2023 | Update personal protective equipment for all fire districts in Benton County.
ALL | ALL Benton County Fire Districts-Departments | Resource & Capability Enhancements | 2023 | Obtain additional funding for training and necessary training equipment and supplies for all fire districts in Benton County.
SPA 1 | Albany Fire Department | Resource & Capability Enhancements | 2023 | Obtain funding for a Type III wildland engine for the Albany Fire Department.
SPA 1 | Corvallis Fire Department | Infrastructure Enhancements | 2023 | Activate Fire Station #5 at 4950 NW Fair Oaks Drive
SPA 1 | Corvallis Fire Department | Resource Enhancement | 2023 | Develop more water sources for Fire Station #6, 544 NW Lewisburg Ave, to access- current sources are a water tank on Raintree Drive and Vineyard Mountain Community swimming pool
SPA 5 | Alsea Rural Fire & Protection District | Resource & Capability Enhancements | 2023 | Obtain funding for an updated water tender and structural engine for the Alsea Rural Fire Protection District.
SPA 4 | Blodgett-Summit Rural Fire Protection District | Resource & Capability Enhancements | 2023 | Obtain funding for an updated Type 1 engine for the Blodgett-Summit Rural Fire Protection District.
SPA 4 | Blodgett-Summit Rural Fire Protection District | Fire Prevention, Education & Mitigation | 2023 | Marval Road & Marval Place- Bridge replacement, Road Widening (1 mile), additional pull-outs. | There are 8 residences on the S-side of the bridge that could be cutoff from fire service and evacuation in the event of a wildfire.
SPA 4 | Blodgett-Summit Rural Fire Protection District | Infrastructure Enhancements | 2023 | Station 600- enlargement of the infrastructure to support larger vehicles and storage
SPA 4 | Blodgett-Summit Rural Fire Protection District | Infrastructure Enhancements | 2023 | Station 601- paving and drainange addition for the front apron of the facility
SPA 4 | Blodgett-Summit Rural Fire Protection District | Resource Enhancement | 2023 | Additional Water Storage tank in the district | Station 600 has a 3600 gallon tank. A larger tank somewhere else in the District would be good planning for low river levels during wildfire season.
SPA 3 | Hoskins-Kings Valley Rural Fire Protection District | Resource Enhancement | 2023 | Obtain funding for an updated engine for the Hoskins-Kings Valley Rural Fire Protection District.
SPA 3 | Hoskins-Kings Valley Rural Fire Protection District | Infrastructure Enhancements | 2023 | Obtain funding for a fire hall expansion for the Hoskins-Kings Valley Rural Fire Protection District.
SPA 3 | Hoskins-Kings Valley Rural Fire Protection District | Resource & Capability Enhancements | 2023 | Support a fuel source initiative to support the Hoskins-Kings Valley Rural Fire Protection District efforts due to loss of local fuel supplier.

## Committee's (hidden)
Community Advisory Co. | First | Last | Association | Position | Contact Email
| Bill | Dunn | Dunn and Company Chipping Company | Owner
| Jeff | Stewart | Ridgewood Estates Firewise Community | Firewise Chair
| Mary | Peterson | Wren Firewise Community | Firewise Chair
| Joe | Heaney | Vineyard Mountain Firewise Community | Firewise Chair
| Greg | Hayes | Vineyard Mountain Water District | Director
| Fernando | Henriques | Vineyard Mountain Road District
| Anne | Fairbrother | Pioneer Village Firewise Community | Firewise Chair
| Maureen | Puettman | Chinook Firewise Community | Firewise Chair
| Carrie | Berger | Skyline West (Corvallis) Firewise Community | Firewise Chair
| Evelyn | Lee | South Benton Firewise Community | Firewise Chair
| Martin | Fitzpatrick | Brownly-Marshall Road District | President
| Sunia | Yang | Brownly-Marshall Road District
| Kate | Hunter-Zaworski | Oakwood Heights Road District
| Karen | Rosenberg
| John | Taylor | Oak Creek Valley
| Ann | Eissinger | Oak Creek Valley | Organizer
| Bart | Spiller | Soap Creek | SC Board Member
| Mike | Thomas | Wren Citizen Advisory Committee | Member
| Liz | Brooks | South Benton Citizen Advisory Committee | Member
| Phillip | Sollins
| David | Dowrie | Planning Commission | Member
Technical Advisory Co. | First | Last | Association | Position | Contact Email | Column1
| Michael | Ahr | Benton Soil and Water Conservation District | Coordinator of Invasive Species Prgm & Willamette Mainstem Coop | michael@bentonswcd.org
| Frederick | Pfund | Starker Forest Company | Vice President- Forestry
| Nathan | Nystrom | Hull-Oakes Company | Forester
| Donald | Irons | Weyerhaeuser Company
| Amanda | Rau | Oregon State University College of Forestry | Regional Wildland Fire Specialist | amanda.rau@oregonstate.edu
| Aaron | Groth | OSU Extension | Regional Wildland Fire Specialist | aaron.groth@oregonstate.edu
| Jim | Johnson | OSU Extension | Emeritus Professor of Forestry
| Brad | Withrow-Robinson | OSU Extension | Forestry & Natural Resources Extension Agent for Benton-Linn-Polk Counties
| Tom | Miller | Philomath Rural Fire Protection District (RFPD) | Fire Chief | chancy.ferguson@philomathfire.com | Replace with Chancy Ferguson
| Rich | Saalsaa | Philomath Rural Fire Protection District (RFPD) | Fire Deputy Chief | rich.saalsaa@philomathfire.com | Position Change
| Ryan | Van Leuven | Alsea RFPD | Fire Chief | rkvanleuven@gmail.com
| Rick | Smith | Monroe RFPD | Fire Chief | cbarnes@monroerfpd.org | Replace with Chris Barnes
| Adam | Ryan | Hoskins-Kings Valley RFPD | Fire Chief | adamdryan@gmail.com
| Aaron | Harris | Adair RFPD | Fire Chief | Aaron@adair-rural-fire.com
| Dave | Feinburg | Blodgett-Summit RFPD | Fire Chief | adamdryan@gmail.com
| Shane | Wooton | Albany Fire Department | Fire Chief | Shane.Wooton@cityofalbany.net
| Cary | Vonasek | Tangent Fire | Fire Chief | Jstearns@tangetfire.com | Replace with Jim Stearns
| Ben | Janes | Corvallis Fire Department | Fire Chief | Ben.janes@corvallisoregon.gov
| Kevin | Fulsher | Corvallis Fire Department | Deputy Fire Chief | Kevin.Fulsher@corvallisoregon.gov
| Chad | Carter | American Red Cross |  |  | Replace with current area rep
| Jonathon | Jones | Oregon State Fire Marshall | State Fire Marshal
| Jason | Cane | Oregon State Fire Marshall | Deputy State Fire Marshal | jason.cane@osp.oregon.gov
| Dave | Busby | City of Corvallis | Fire Emergency Planning Manager | dave.busby@corvallisoregon.gov
Oregon Department Of Forestry
Oregon Department Of Forestry
Oregon Department Of Forestry
Northwest Oregon Interagency Fire Management NW Oregon District BLM Oregon Coast Refuge Complex USFWS, Siuslaw and Willamette NF
Northwest Oregon Interagency Fire Management NW Oregon District BLM Siuslaw and Willamette NF
U.S. Fish and Wildlife Service
USDA-Natural Resources Conservation Service
Republic Services
Benton County Comm Dev Dept
| Bryan | Lee | Benton County Sheriff's Office | Emergency Manager | bryan.lee@co.benton.or.us
| Chelsea | Chytka | Benton County Sheriff's Office | Emergency Management Coordinator | chelsea.chytka@co.benton.or.us
Benton County Public Works
Benton County Public Works
Benton County Natural Areas, Parks And Events Department
| Kevin | Higgins | Benton County Sheriff's Office | Special Services Supervisor | kevin.higgins@co.benton.or.us
| Trask | Hodgson | Oregon Department of Forestry | Community Wildfire Forester | Trask.E.HODGSON@odf.oregon.gov
| Leo | Willianson | Oregon Department of Forestry | Protection Unit Forester- Philomath | Leo.H.WILLIAMSON@odf.oregon.gov